## Instructions
Last Update: September, 2017
Instructions for Using the Project Scheduling Templates
Research Project Management
Memorial University of Newfoundland
Bruneau Centre for Research and Innovation P.O. Box 4200
St. John's, NL. A1C 5S7
Sequencing Template: The purpose of the Project Sequencing template is to plan the project timeline in regards to the anticipated start and end dates of the project objectives, activities, and tasks.
In planning a project schedule, the recommended approach is to first take your list of objectives/activities/tasks and sequence them in their natural order of occurrence by identifying the start and end dates of each.
To aid in sequencing of objectives/activities/Tasks researchers should identify all the constraints and dependencies that will impact the timing of work items.
Once the factors that may affect the timing of work items are recognized, the work item durations, or the planned start and end dates can be identified.
Gantt Chart Template:
A Gantt Chart is a visual representation of your work items against a time line. It provides researchers the ability to easily communicate a project schedule, and aids in the monitoring of project progress.
Upon completion of the 'Sequencing template' a Gantt chart will automatically populate within the 'Gantt Chart Template' Tab. The only fields that researchers need to update on this Tab are the 'Actual End Date' and '% Complete' fields. Completion of these fields will aid in the monitoring of project progress.
The current date is represented by a vertical red line within the Gantt chart.
For a more detailed overview of the 'Gantt Chart Template' functionalities it is recommended that researcher review the associated User Guide for the Scheduling Templates.
Milestone Template: Milestones are reference points in the project’s progress that represent accomplishment. For example, approval from an ethics committee or regulatory body, accomplishment of a deliverable/objective, or indicator or a major reporting requirement. The 'Milestone Template' provides a format for the researcher to document anticipated project milestones. The milestones for a project should reflect a clear list of events that incrementally build to the project completion. Having a well-documented milestone list will aid in the monitoring of project progress once started.
Milestone can be reflected in the Gantt Chart by inserting them as line items within the 'Sequencing Template'.
Glossary: The glossary provides definitions of terms used within the templates.
Settings:
This tab stores settings that are required for functionalities of the Gantt Chart. Researchers do not need to use this tab. General Template User Instructions:
▪ Make changes to the start date, planned end date and the actual end date. Be sure to insert dates using the format "dd-mmm-yyyy". Do not forget to enter your actual end date.
▪ When making changes to the percent completed be sure to enter only quarters i.e "0%, 25%, 50%, 100%"
▪As in the 'Scope Templates' numerical and colour coding is used in these templates to identify objectives/deliverables, activities, and task. i.e. 1.0 - Represents an identified project objective or deliverable (Grey) 1.1 - Represents an activity associated with that objective (White) 1.1.1 - Represents a task associated with that activity (Red)
For more detailed guidance on the use of these templates, please see the associated User Guide available on the Research Project Management Website
If you have any questions, or have found any errors within this Template package, please feel free to contact us through our website: https://research-tools.mun.ca/rpm/
Copyright © 2017 Memorial University of Newfoundland

## Sequencing Template
Research Project Name:
Project Investigator:
Project Manager (If Applicable):
Start Date:
End Date:
Objective/Activity/Task # | Objective/Activity/Task Title | Planned Start Date | Planned Completion Date | Constraints/Dependencies
Research Project Management
Tools and Templates
https://research-tools.mun.ca/rpm/
Sequencing Template

## Milestone Template
Research Project Name:
Project Investigator:
Project Manager (If Applicable):
Start Date:
End Date:
Milestone # | Milestone Description | Planned Completion Date | Indicator of Achievement/Additional Comments
Research Project Management
Tools and Templates
https://research-tools.mun.ca/rpm/
Milestone Template

## Glossary
Glossary of Terms and Definitions
Constraints | A constraint, in project management, is any restriction that defines a project's limitations; the scope, for example, is the limit of what the project is expected to accomplish.
Dependencies | Dependencies are the relationships of the preceding tasks to the succeeding tasks. Tasks may have multiple preceding tasks and multiple succeeding tasks.
Indicator of Achievement | This is an indication as to when the Milestone has been completed
Percent Completed | This is how much of the Objective/Activity/Task that you have completed. For this worksheet values such as "0%, 25%,50%, 75% , and 100%" can be used.

## Settings
Please do not change these values!
Name | Value | Description
DateOffset |  | Used by the scrollbar. Do not manually change.
WeekStartType | 1 | Sets the day of the week to display as the start of the week (e.g. 2 = Monday).
GanttNoOfYears | 7 | Sets the date coverage of the Gantt chart (i.e. the latest date that can be displayed).
ShowFY | FALSE | Toggles between splitting years into Financial Years (e.g. 2009/10) or Calendar Years (e.g. 2009). Set to TRUE if you want to display Financial Years.